## Sheet1
Task | Days | Hengsu comment
AEF | (Working Days)
different folders issue | 1
run single task issue | 0.5 | I assume this issue occurred by incorrect initial registration, so it may take half day.
compatible with older version | 2 | We request this to be compatible with current version. Not with all older versions. So this may be easier than you expect.
context menu issue. | 0.5 | Contextr menu did work in old versions, so it may be easier and other context menu issues will be fixed in same manner.
modification not saved. | 1
FileEncrypt
compatible with older version | 2 | As noted in line#6, it may be easier.
context menu issue | 0.5
Command line tool, FED.exe(I did not write about this because there is no request&hep about this)
compatible with older version(so maybe it is just as same as current one, but it should be compatible with above updated AEF and FileEncrypt) | 2 | as same as line#10
Encryption self extracting archive file feature | 9
FileDelete
compatible with Win10 and earlier | 2 | You have developed File delete API version, and it should be used as file delete engine in this, so I reduce this task.
delete log | 0.5 | Same as above.
Would you please add the "Secure Delete Freespace" button on FileDelete application, which curretly sits on DiskDelete application? sorry, but without extra charge?
Command line tool DMF.exe (I did not write about this because there is no request&hep about this)
compatible with Win10 and earlier(maybe it is just as same as current one) | 2 | Due to the existing API version and line#17, I reduce this
DiskDelete
compatible with Win10 and earlier | 3
GPT MBR disk aware | 6
delete log should be recored in certain place or system event | 1
delete bug*1 securely delete entire disk. Look at "delete bug" | 2
DiskDeleteBootdisk
UEFI BIOS compatible boot disk | 6
GPT MBR aware disk delete tool run on above | 3 | I assumethis is related with Ine#23 and both can use same delete engine, so I reduce this. Please comment if this is wrong.
delete log should be recored in certain places in boot USB or other externals | 1
bootdisk creation | 3
delete bug*1 | 1
49